## CapEx Log 2024-2026
CAPITAL PLAN & CAPEX LOG — 2024–2026
Cascade Ridge Apartments ¦ Total Budget: $4,200,000 ¦ Reserve Account: First Commerce Bank XXXX-8824 ¦ Status as of September 30, 2024
Project ID | Category | Description | Phase | Budget ($) | Draw #1 ($) | Draw #2 ($) | Draw #3 ($) | Total Drawn ($) | Remaining ($) | Start Date | Completion Date | Contractor | Status
CR-2024-001 | Unit Interior Renovation | Phase 1 — Batch 1: Units 101-148 (24 units @ $24,500) | Phase 1 | 588000 | 300000 | 288000 |  | 588000 | 0 | 2024-04-01 | 2024-06-30 | Alpine Construction Partners LLC | Complete
CR-2024-002 | Unit Interior Renovation | Phase 1 — Batch 2: Units 201-228 (9 units @ $24,800) | Phase 1 | 223200 | 223200 |  |  | 223200 | 0 | 2024-07-01 | 2024-08-15 | Alpine Construction Partners LLC | Complete
CR-2024-003 | Unit Interior Renovation | Phase 1 — Batch 3: Units 301-316 (8 units @ $25,050) | Phase 1 | 200400 | 200400 |  |  | 200400 | 0 | 2024-08-01 | 2024-09-15 | Alpine Construction Partners LLC | Complete
CR-2024-004 | Unit Interior Renovation | Phase 1 — Batch 4: Units 401-448 (7 units @ $25,000) | Phase 1 | 175000 |  |  |  | 0 | 175000 | 2024-10-01 | 2024-11-30 | Alpine Construction Partners LLC | In Progress
CR-2024-005 | Unit Interior Renovation | Phase 1 — Batch 5 (Final 8 units @ $25,000) | Phase 1 | 200000 |  |  |  | 0 | 200000 | 2024-11-15 | 2024-12-15 | Alpine Construction Partners LLC | Scheduled
CR-2024-006 | LED Lighting Retrofit | Common area LED retrofit (all buildings, parking, corridors) | Phase 1 | 8400 | 8400 |  |  | 8400 | 0 | 2024-02-01 | 2024-03-15 | Sparks Electric LLC | Complete
CR-2024-007 | Exterior / Curb Appeal | Monument signage, entry redesign, landscaping | Phase 1 | 85000 | 42500 |  |  | 42500 | 42500 | 2024-09-01 | 2024-11-30 | SignWorks Co. / GreenThumb Landscape | In Progress
CR-2024-008 | Exterior Paint | Building exteriors: Buildings 1-5 (two coats) | Phase 1 | 62000 |  |  |  | 0 | 62000 | 2024-10-15 | 2024-12-01 | Alpine Construction Partners LLC | Scheduled
CR-2024-009 | Parking Lot Maintenance | Seal coat and re-stripe all 312 parking spaces | Phase 1 | 22000 |  |  |  | 0 | 22000 | 2024-11-01 | 2024-11-30 | Asphalt Plus LLC | Scheduled
CR-2025-001 | Clubhouse Renovation | New finishes, co-working lounge, package room buildout | Phase 2 | 185000 |  |  |  | 0 | 185000 | 2025-03-01 | 2025-05-31 | Summit Interior Group | Planned
CR-2025-002 | Fitness Center Upgrade | New equipment package, flooring, mirrors, AV system | Phase 2 | 95000 |  |  |  | 0 | 95000 | 2025-04-01 | 2025-05-15 | FitBuild Inc. | Planned
CR-2025-003 | Pool Deck / Outdoor Amenities | Pool resurfacing, new furniture, updated grills, landscaping | Phase 2 | 120000 |  |  |  | 0 | 120000 | 2025-05-01 | 2025-06-30 | AquaWorks CO / GreenThumb | Planned
CR-2025-004 | Unit Interior Renovation | Phase 2 — 32 units (concurrent with amenities) | Phase 2 | 800000 |  |  |  | 0 | 800000 | 2025-01-15 | 2025-09-30 | Alpine Construction Partners LLC | Planned
CR-2026-001 | Unit Interior Renovation | Phase 3 — Final 40 units @ $25,000 | Phase 3 | 1000000 |  |  |  | 0 | 1000000 | 2026-01-15 | 2026-06-30 | TBD | Planned
CR-2026-002 | Ongoing Mechanical / Preventive | HVAC, plumbing, roof repairs, electrical (3-yr total) | All Phases | 240000 | 27000 | 27000 | 29000 | 83000 | 157000 | 2024-03-15 | 2026-12-31 | Various | Ongoing
CR-ALL-001 | Soft Costs / Project Mgmt | Legal, permits, project management, contingency | All Phases | 396400 | 70000 |  |  | 70000 | 326400 | 2024-03-15 | 2026-12-31 | Caldwell & Pierce / Alpine | Ongoing
TOTALS |  |  |  | 4400400 | 871500 | 315000 | 29000 | 1215500 | 3184900

## Summary by Phase
CAPITAL PLAN SUMMARY BY PHASE
Phase | Description | Total Budget | Drawn to Date | % Complete | Remaining Budget | Target Completion
Phase 1 | 48 unit renovations + exterior + curb appeal | 1384800 | 1062500 | 76.73% | 322300 | December 2024
Phase 2 | 32 unit renovations + all amenity upgrades | 1200000 | 0 | 0% | 1200000 | September 2025
Phase 3 | 40 unit renovations | 1000000 | 0 | 0% | 1000000 | June 2026
All Phases | Mechanical, contingency, soft costs, project mgmt | 636400 | 153000 | 24.04% | 483400 | December 2026
TOTAL | Complete Capital Plan | 4221200 | 1215500 | 28.8% | 3005700 | December 2026