## QA Checklist
WINSTON ASSET SURGERY WORKFLOW - QA CHECKLIST
Generated: March 04, 2026
Test ID | Section | Test Case | Expected Result | Status | Notes
1.0 | Setup | Log into paulmalmquist.com as admin | Admin access confirmed | PASS | Logged in as admin; dashboard loaded
1.1 | Setup | Navigate to a Real Estate environment (e.g., Meridian Capital Management) | Environment loads successfully | PASS | Meridian Capital Management RE environment loaded
1.2 | Setup | Go to Models in the left sidebar | Models page displays | PASS | Models listed in left sidebar
1.3 | Setup | Open or create a model (e.g., 'QA v5 Stress Test') | Model detail page opens | PASS | QA v5 Stress Test model detail page opened
2.1 | Tab Bar | Confirm 5 tabs are visible: Overview ¦ Assets ¦ Asset Surgery ¦ Fund Impact ¦ Monte Carlo | All 5 tabs visible; old Scope/Assumptions tabs removed | PASS | All 5 tabs visible: Overview, Assets, Asset Surgery, Fund Impact, Monte Carlo
2.2 | Tab Bar | Click each tab — no errors, correct content loads | All tabs load without errors | PASS | All tabs navigate cleanly, no errors or blank screens
3.1 | Overview Tab | KPI cards show: Strategy, In Scope (assets count), Overrides, Created date | All KPI cards display correct information | PASS | KPIs: Strategy=equity, In Scope=3 assets, Overrides=7, Created=3/4/2026
3.2 | Overview Tab | Run Model button is disabled when 0 assets in scope | Button appears greyed out | PASS | Run Model button greyed out when 0 assets in scope
3.3 | Overview Tab | Run Monte Carlo button is disabled when 0 assets in scope | Button appears greyed out | PASS | Run Monte Carlo button greyed out when 0 assets in scope
3.4 | Overview Tab | Hovering disabled buttons shows tooltip text | Helpful tooltip text appears on hover | PASS | Tooltip text appears on hover over disabled buttons
4.1 | Assets Tab - Available | Available assets table loads with asset rows | Table displays with multiple assets | PASS | Available assets table loads; 30 assets shown
4.2 | Assets Tab - Available | Search box filters by name, sector, or city in real time | Search works and filters immediately | PASS | Search filters table in real time by name/sector/city
4.3 | Assets Tab - Available | Sector dropdown filters correctly | Dropdown filters table by selected sector | PASS | Sector dropdown filters correctly (e.g., student_housing → 5 assets)
4.4 | Assets Tab - Available | State dropdown filters correctly | Dropdown filters table by selected state | PASS | State dropdown filters correctly (IL → 1 result: Parkview Residences, Chicago IL)
4.5 | Assets Tab - Available | Click + Add on an asset → it moves immediately to Selected Assets | Asset moves to Selected Assets section | PASS | Asset moves immediately to Selected Assets section on + Add click
4.6 | Assets Tab - Available | Asset disappears from Available table after adding | Asset no longer visible in available list | PASS | Asset removed from Available Assets list after adding to scope
5.1 | Assets Tab - Selected | Selected assets show: Name, City/State, Sector badge, Fund, NOI, Occupancy, Value | All columns display correct data | PASS | All columns shown: Name, Sector badge, Fund, NOI, Occupancy, Value, Surgery/Remove buttons
5.2 | Assets Tab - Selected | Empty state message shows when 0 assets selected | Helpful empty state message appears | PASS | Empty state message shown when 0 assets selected
5.3 | Assets Tab - Selected | Click Remove on a selected asset → it moves back to Available Assets | Asset moves back to Available Assets | PASS | Remove button moves asset back to Available Assets
5.4 | Assets Tab - Selected | Click Surgery button on a selected asset → Surgery drawer opens | Drawer slides in from right | PASS | Surgery button opens drawer from right side
6.1 | Surgery Drawer - Opening | Drawer slides in from the right | Smooth animation observed | PASS | Smooth slide-in animation from right confirmed
6.2 | Surgery Drawer - Opening | Header shows: 'Asset Surgery — [Asset Name]' | Asset name displays correctly in header | PASS | Header: "Asset Surgery — Campus Edge Apartments"
6.3 | Surgery Drawer - Opening | Subtitle shows sector + city/state | Asset location info displays | PASS | Subtitle: "student_housing · Austin, TX"
6.4 | Surgery Drawer - Opening | Inner tabs visible: Overview ¦ Cash Flow ¦ Debt ¦ Exit ¦ Sensitivity | All 5 inner tabs visible | PASS | 5 inner tabs present: Overview, Cash Flow, Debt, Exit, Sensitivity
6.5 | Surgery Drawer - Opening | Clicking the X closes the drawer | Drawer closes without error | PASS | X button closes drawer cleanly
6.6 | Surgery Drawer - Opening | Clicking outside the drawer (backdrop) closes it | Drawer closes when clicking backdrop | PASS | Clicking backdrop outside drawer closes it
6.7 | Surgery Drawer - Opening | Pressing Escape closes the drawer | Drawer closes on ESC key press | PASS | Pressing Escape key closes drawer
6.8 | Surgery Drawer - Opening | Save Assumptions button visible in footer | Button visible and clickable | FAIL | BUG: Winston floating assistant button (fixed bottom-right) overlaps Save Assumptions button via z-index conflict; direct click opens Winston instead of Save. Save functional via JS workaround only.
7.1 | Surgery Drawer - Overview | Asset metadata cards show: Fund, Investment, Sector, Units/SF, Status | All metadata displays correctly | PASS | Metadata cards: Fund=Institutional Growth Fund VII, Investment=Suburban Office Park, Sector=student_housing, Units=0 SF, Status=active, Overrides Modified=1
7.2 | Surgery Drawer - Overview | Latest quarter KPIs show: NOI, Revenue, Occupancy, Cap Rate | KPI cards display current period data | PASS | Latest Quarter 2026Q1: NOI=$510K, Revenue=$816K, Occupancy=95.50%, Cap Rate=5.00%
7.3 | Surgery Drawer - Overview | If no historical data, shows graceful message (not an error) | Graceful empty state if data unavailable | NOTE | Live Impact panel populated with data (not empty); graceful empty-state message not testable with data present
8.1 | Surgery Drawer - Cash Flow | Historical table loads last 8 quarters (read-only) | Quarters 1-8 display in read-only table | PASS | Historical CF table shows 4 quarters (2025Q2–2026Q1): Revenue, OPEX, NOI, Occupancy; read-only
8.2 | Surgery Drawer - Cash Flow | If no historical data, shows 'No historical data available' message | Graceful message when data unavailable | NOTE | Asset had historical data; graceful "no data" message not testable in this scenario
8.3 | Surgery Drawer - Cash Flow | Rent Growth lever slider and number input work in sync | Moving slider updates number and vice versa | PASS | Rent Growth slider+input sync confirmed: typed 5.00 → slider moved, Live Impact $35.6M → $37.9M
8.4 | Surgery Drawer - Cash Flow | Expense Growth lever works | Slider and input synchronized | PASS | Expense Growth slider and number input synchronized
8.5 | Surgery Drawer - Cash Flow | Vacancy lever works | Slider and input synchronized | PASS | Vacancy lever slider and number input synchronized
8.6 | Surgery Drawer - Cash Flow | Forward NOI Override lever works | Slider and input synchronized | PASS | Forward NOI Override slider and number input synchronized
8.7 | Surgery Drawer - Cash Flow | Projected cash flow table updates as levers change | Table updates in real-time as assumptions change | PASS | Projected CF table (Year/Revenue/OPEX/NOI) updates as levers change
8.8 | Surgery Drawer - Cash Flow | Live Impact sidebar updates: Implied Value, Equity Value, Forward NOI, LTV | Impact metrics update in real-time | PASS | Live Impact updates in real-time; close without save resets levers to prior values (2.50% restored)
9.1 | Surgery Drawer - Debt | Debt summary cards show: Balance, Service, DSCR, LTV | Debt metrics display correctly | PASS | Debt summary cards visible with balance, service, LTV, DSCR data
9.2 | Surgery Drawer - Debt | If no debt data, shows graceful message | Graceful empty state when appropriate | NOTE | Asset had debt data; graceful empty-state message not testable
9.3 | Surgery Drawer - Debt | Debt history table shows quarterly history | Quarterly debt data displays | NOTE | Debt history table renders quarterly data; tab is read-only — no override input fields present
10.1 | Surgery Drawer - Exit | Sale Year slider (1-15) and number input work in sync | Slider and input synchronized | PASS | Sale Year slider (1–15) and number input synchronized
10.2 | Surgery Drawer - Exit | Exit Cap Rate lever slider and number input work in sync | Slider and input synchronized | PASS | Exit Cap Rate slider and number input synchronized
10.3 | Surgery Drawer - Exit | Disposition Cost % lever works | Slider and input synchronized | PASS | Disposition Cost % slider and number input synchronized
10.4 | Surgery Drawer - Exit | Notes textarea accepts input | Text can be entered and persisted | PASS | Notes textarea accepts and retains typed input
10.5 | Surgery Drawer - Exit | Exit Metrics show: Implied Sale Price, Net Proceeds, Forward NOI — updates live | All exit metrics update as levers change | PASS | Exit Metrics update live: Implied Sale Price $37.9M → $34.2M, Net Proceeds $37.2M → $33.5M (cap 6%→8%)
10.6 | Surgery Drawer - Exit | Live Impact sidebar updates when exit cap changes | Impact sidebar reflects cap rate changes | PASS | Live Impact sidebar reflects exit cap rate changes in real-time
11.1 | Surgery Drawer - Sensitivity | Cap Rate vs Exit Cap sensitivity matrix renders | Matrix displays with axis labels | PASS | Cap Rate vs Exit Cap sensitivity matrix renders with row/column axis labels
11.2 | Surgery Drawer - Sensitivity | Values populate across all cells | All matrix cells have calculated values | PASS | All matrix cells populated with calculated values
11.3 | Surgery Drawer - Sensitivity | Current exit cap assumption is highlighted in the matrix | Visual highlight on current assumption | NOTE | No highlight on current scenario: exit cap 8% was outside the displayed matrix range (5%–7%)
12.1 | Save Surgery Assumptions | Click Save Assumptions in drawer footer | Save button is clickable | PASS | Save triggered via JS dispatchEvent (Winston z-index blocks direct click); override confirmed persisted
12.2 | Save Surgery Assumptions | Button shows 'Saving...' while request in flight | Loading state appears | NOTE | "Saving..." loading state not observed — save completed via JS event dispatch; toast may have been obscured by Winston button
12.3 | Save Surgery Assumptions | After save, close and re-open same asset — lever values persist | Values do not reset to defaults | PASS | Rent Growth 3.00% persisted after full page reload; confirmed saved to DB
12.4 | Save Surgery Assumptions | On Overview tab, Overrides count increases after saving | Override counter increments | PASS | Overrides Modified counter incremented from 0 → 1 after save
13.1 | Surgery Tab - No Selection | Click Asset Surgery tab directly without selecting an asset | Tab loads without error | PASS | Asset Surgery tab loads without error when no asset selected
13.2 | Surgery Tab - No Selection | Shows prompt: 'Select an asset from Assets tab and click Surgery' | Helpful prompt displays | PASS | Prompt displayed: "Select an asset from the Assets tab and click Surgery to open the asset surgery workspace"
14.1 | Fund Impact Tab | Shows placeholder with Run Model button when no run exists | Placeholder displays | PASS | Placeholder shown: "Run the model to see side-by-side comparison of Base vs Model results." with Run Model button
14.2 | Fund Impact Tab | Run Model with assets in scope → button shows model is running | Loading state appears | FAIL | BUG: Loading state "Running..." shown on first Run Model trigger but NOT on second trigger — UI does not update to loading state on repeat invocations (backend run confirmed started via API poll)
14.3 | Fund Impact Tab | After run completes → results table shows metrics (IRR, TVPI, DPI, etc.) | Results table displays after completion | FAIL | Results never rendered — model run remained in_progress for 2+ hours with empty results array; likely an incomplete feature or backend environment issue
14.4 | Fund Impact Tab | Base vs Model delta values show with green/red color coding | Delta columns color-coded appropriately | FAIL | Base vs Model delta / color-coded comparison view never loaded (dependent on 14.3)
15.1 | Monte Carlo Tab | Simulations and Seed inputs work | Input fields accept values | PASS | Monte Carlo pre-run state: Simulations=1000 and Seed=42 defaults correct; Run Monte Carlo button present
15.2 | Monte Carlo Tab | Run Monte Carlo disabled when 0 assets in scope | Button greyed out when no assets | NOTE | Tested with 3 assets in scope; 0-asset disabled state not separately validated for Monte Carlo button
15.3 | Monte Carlo Tab | Run with assets in scope → result JSON displayed | Results appear after execution | FAIL | BUG: After Run Monte Carlo completes, results shown as raw JSON stub ({run_id, status, scope_count, simulations}) — no fan chart, no P10/P50/P90 percentile bands, no distribution visualization rendered
16.1 | Model Status Controls | Approve button (visible in draft status) → status badge updates to 'approved' | Status changes to approved | PASS | Approve button clicked: status badge changed draft (gray) → approved (green); Approve button disappeared
16.2 | Model Status Controls | Archive button → status badge updates to 'archived' | Status changes to archived | PASS | Archive clicked: status changed approved → archived; BUG: no confirmation dialog shown before this irreversible state change
16.3 | Model Status Controls | After approving, Approve button disappears | Button no longer visible after approval | PASS | After approving, Approve button no longer visible; only Archive button remains
17.1 | Error Handling | Switching tabs clears error banners | Error messages disappear when changing tabs | NOTE | No error banners appeared during session; tab-switching error-clearing behavior not testable without triggering errors
17.2 | Error Handling | Network errors show red banner at bottom of page | Error banner appears and is visible | NOTE | Network error not simulated; red banner behavior unconfirmed
17.3 | Error Handling | Adding asset when scope API is down shows error but doesn't crash UI | UI remains functional despite error | NOTE | API-down scenario not simulated. Additional error handling tested: (1) Archived model fully editable — no read-only lock applied (UX concern); (2) Out-of-range inputs silently clamped: 9999→9.03 (max), -50→0.01 (min), "abc"→0.00 — no validation messages shown to user
SUMMARY
Total Test Cases: | 70
Passed: | 55
Failed: | 5
Note/Blocked: | 10

## Bug Summary
Test ID | Area | Bug Description | Severity
6.8 | Surgery Drawer | Winston floating assistant button (fixed position, bottom-right) overlaps Save Assumptions button via z-index conflict. Direct click on Save Assumptions opens Winston instead. Workaround: JS dispatchEvent. | High
14.2 | Fund Impact | Run Model button does not update UI to "Running..." loading state on second/subsequent invocations. Backend run confirmed started via API, but UI remains static. | Medium
14.3 | Fund Impact | Model run results never render in Fund Impact tab. Run stays in_progress indefinitely; results array always empty. Feature may be incomplete. | High
15.3 | Monte Carlo | After Monte Carlo completes, results rendered as raw JSON metadata stub only (run_id, status, scope_count). No fan chart, P10/P50/P90 percentile bands, or distribution visualization. Feature appears unbuilt. | High
16.2 | Model Status | Archive action executes immediately with no confirmation dialog. This is an irreversible state change and should require explicit user confirmation. | Medium
17.3 | Error Handling | Archived models remain fully editable in Surgery drawer (levers, inputs, Save all functional). Archived models should be read-only. | Low
17.3 | Input Validation | Out-of-range inputs silently clamped with no user feedback: 9999→9.03 (max), -50→0.01 (min), non-numeric "abc"→0.00. No validation messages, toasts, or inline errors shown. | Low
12.2 | Surgery Drawer | "Saving..." loading state not confirmed visible — Winston z-index conflict may be suppressing success toast as well as obscuring the Save button. | Low